Timeline

This timeline is to keep you on track to complete the project.

The only hard deadlines are the brief report due on the 23/09, and the final report due on the 11/11. If you are ahead or a little behind the weekly schedule, that is completely fine.

|  |  |  |
| --- | --- | --- |
| Task | Weeks allocated | Completion Date |
| 1D spatial pattern finding | 1 | 02/09 |
| 2D spatial pattern finding | 1 | 09/09 |
| 1D spectral pattern finding | 1 | 16/09 |
| 2D spectral pattern finding | 1 | 23/09 |
| Brief report | - | 23/09 |
| Uncalibrated depth maps | 2 | 7/10 |
| Calibrated depth maps (only if ahead of schedule) \* | - |  |
| Extension project | 3 | 28/10 |
| Report due | - | 11/11? |

\* Only if running ahead of schedule. I would rather you use your new knowledge and skills to do an extension project which interests you.